INTERNSHIP PROJECT / WEEK 2 AI Customer Calling Agent Core Voice Conversation Engine Development Progress Document Voice loop implemented ¦ 65 unit tests passing ¦ Live call and streaming STT pending access

WEEK 2 OF 4 ¦ DAYS 6 TO 10 ¦ VERSION 1.0 ¦ 31 OCTOBER 2026

| PREPARED BY | Sumyai Butt |
| --- | --- |
| PROJECT | AI Customer Calling Agent |
| DOCUMENT TYPE | Week 2 Development Progress Document |
| WEEK COVERED | Week 2 - Core Voice Conversation Engine (Days 6 to 10) |
| ENVIRONMENT | Python 3.12.10 on Windows (win32) |
| RELATED PLAN | AI_Customer_Calling_Agent_Development_Plan.docx (unchanged) |
| REPOSITORY STATE | New Week 2 files added; Week 1 files updated; nothing deleted |

Prepared for internship supervisor review. This document reports implemented and verified work only. No live phone call has been placed.

Contents

| 1. | Purpose and Context |
| --- | --- |
| 2. | Week 2 Scope and Design Decisions |
| 3. | Week 2 Architecture |
| 4. | Conversation Engine and Escalation |
| 5. | Voice Pipeline |
| 6. | Implementation |
| 7. | Testing and Results |
| 8. | Blockers and Access Checklist |
| 9. | Week 2 Progress Plan |
| 10. | Risks and Mitigations |
| 11. | Deliverables and Acceptance Checklist |
| 12. | Limitations and Deferred Work |
| 13. | Conclusion |
| Appendix A | Setup and Commands |
| Appendix B | Week 2 Simulated Call Transcript |
| Appendix C | Week 2 Test Results |
| Appendix D | GitHub Change List |

Week 2 development progress document for the AI Customer Calling Agent internship project. It reports only work that was implemented, executed and verified in this environment. No live phone call was placed, and no speech-recognition engine is connected.

# Document Control

| Item | Detail |
| --- | --- |
| Project name | AI Customer Calling Agent |
| Document type | Week 2 Development Progress Document |
| Prepared by | Sumyai Butt |
| Programme | Internship project, four-week development plan |
| Week covered | Week 2 - Core Voice Conversation Engine (Days 6 to 10) |
| Version | 1.0 |
| Date | 31 October 2026 |
| Environment | Python 3.12.10 on Windows (win32) |
| Related document | AI_Customer_Calling_Agent_Development_Plan.docx (unchanged) |
| Previous document | WEEK1_DEVELOPMENT_DOCUMENT.docx (unchanged) |
| Current status | Knowledge base, call session and local voice loop implemented and tested; live call and streaming speech recognition pending access |

# 1. Purpose and Context

## 1.1 Purpose of this document

This document reports what was actually built, run and tested during Week 2 of the AI Customer Calling Agent project. It follows the same rule as the Week 1 report: every component marked as complete exists in the repository and was executed locally, and everything that is not working is labelled as planned, deferred or blocked.

Week 2 in the master plan is the week where the voice conversation engine is built. In this environment there is still no telephony account, no speech-recognition credential and no test phone number. The work was therefore split into two parts: everything that can be built and proven without those accounts was completed, and the parts that need a live audio stream were documented as blocked.

## 1.2 Relationship to the overall development plan

The existing plan (AI_Customer_Calling_Agent_Development_Plan.docx) remains the master schedule and was not modified. It defines Week 2 around the core voice conversation engine: streaming speech-to-text, the dialogue engine, text-to-speech, natural turn-taking and an end-to-end response target of about 1.5 seconds.

This week delivers the dialogue and session layer that the voice engine depends on: a validated knowledge base, a per-call session with automatic escalation and a handoff summary, and a voice loop with pluggable speech interfaces. The loop is exercised with typed input as the speech-to-text stand-in and the laptop's Windows voice as the output. Streaming speech-to-text, barge-in and latency measurement remain blocked on provider access. Section 8 records that gap and the exact access required.

## 1.3 Week 2 objective

Extend the tested Week 1 decision layer into a call-level conversation engine: approved-knowledge answering, state across turns, automatic escalation when the customer is repeatedly misunderstood, a handoff summary, and a voice input and output loop that can later be connected to real telephony without rewriting the dialogue code.

## 1.4 Progress summary

| Week 2 item | Status | Evidence |
| --- | --- | --- |
| Validated FAQ knowledge base | Complete, verified | src/knowledge_base.py, 14 tests, Section 5 |
| Call session with state across turns | Complete, verified | src/session.py, 12 tests, Section 4 |
| Automatic escalation after repeated misunderstanding | Complete, verified | Three consecutive misses trigger handoff, Section 4.3 |
| Handoff summary for the human representative | Complete, verified | ConversationSession.summary(), Section 4.4 |
| Voice loop with swappable speech interfaces | Complete, verified | src/voice/pipeline.py, 12 tests, Section 5 |
| Spoken replies | Complete locally | Windows SAPI through PowerShell, Section 5.3 |
| Streaming speech-to-text and microphone input | Not completed - blocked on access | Section 8 |
| Telephony test call | Not completed - blocked on access | Section 8 |
| Barge-in and latency measurement | Not completed - needs a real audio stream | Section 12 |
| Automated tests | Complete, verified | 65 tests, 0 failures, Section 7 |
| README and Week 2 document | Complete | This document and README.md |

Honest status statement: the voice loop runs, the call session runs and all 65 automated tests pass. The customer's words in the Week 2 demo are typed, not recognised from audio. The spoken voice is the laptop's built-in Windows voice, not a telephone voice. No telephone call, audio recording or live speech recognition has been performed, and no response-latency figure has been measured.

# 2. Week 2 Scope and Design Decisions

## 2.1 Scope implemented this week

A knowledge base of approved FAQ entries with load-time validation, duplicate detection and a keyword-scoring lookup.

A conversation session that remembers turns, counts consecutive misunderstandings and stores whether the call has been escalated or ended.

Automatic escalation to a human representative after three consecutive misunderstood turns, matching the master plan's rule of two or three attempts.

A one-line handoff summary containing the number of turns, the topics covered and the outcome.

A voice pipeline that takes a transcript, runs the session, and speaks the reply, with speech-to-text and text-to-speech behind interfaces.

A local spoken output back end using the Windows SAPI voice through PowerShell, with a printed fallback when no voice is available.

A simulated-call demo with a fixed script and an interactive mode, plus captured output for evidence.

38 new automated tests, keeping all 27 Week 1 tests passing.

## 2.2 Deliberately deferred

| Deferred item | Reason |
| --- | --- |
| Streaming speech-to-text from a microphone | No STT account or credential in this environment |
| Real telephony inbound and outbound calls | No telephony account, phone number or webhook |
| Barge-in (customer interrupting the agent) | Requires a real audio stream and echo handling |
| End-to-end latency measurement | Cannot be measured without real STT and TTS network calls |
| Urdu and mixed-language speech | Needs an STT model with the target accent coverage |
| CRM, calendar and dashboard integration | Planned for Week 3 in the master plan |
| LLM-based free-form understanding | Rule-based intents are deterministic and need no API key; the plan allows this for the MVP |

## 2.3 Key design decisions

| Decision | Reason |
| --- | --- |
| Keep the rule-based intent layer from Week 1 | Deterministic, explainable and testable without an API key; it also gives a stable baseline for later comparison with an LLM classifier |
| Move FAQ handling into a validated knowledge base | A malformed or duplicate entry now fails at load time instead of producing a wrong answer mid-call |
| Put per-call state in a separate session object | Keeps CustomerSupportAgent focused on one turn; the Week 1 text CLI continues to work unchanged |
| Escalate after three consecutive misses | Matches the plan's escalation rule and prevents the customer being trapped in a fallback loop |
| Define speech-to-text and text-to-speech as small protocols | Real providers can replace the typed and SAPI back ends without touching session or dialogue code |
| Use the built-in Windows voice for local output | No API key, no cost, works offline; it is clearly not a production telephony voice |
| Label typed input as a stand-in everywhere | The report and README must not imply that speech recognition is working |

# 3. Week 2 Architecture

## 3.1 Turn path

Typed words (STT stand-in)
        |
        v
TypedInputSTT.transcribe()          src/voice/stt.py
        |
        v
ConversationSession.handle()        src/session.py
        |
        +--> CustomerSupportAgent.handle_message()    src/agent.py
        |         |
        |         +--> KnowledgeBase.find()           src/knowledge_base.py
        |         +--> sample order store              src/sample_data.py
        |
        +--> fallback counter, escalation flag, turn history
        |
        v
TextToSpeech.speak()                SAPI (PowerShell) or console
        |
        v
Customer hears the reply            (local laptop audio, not telephony)

## 3.2 What is new compared with Week 1

Week 1 had one object, CustomerSupportAgent, which answered one message at a time. Week 2 adds three layers around it: the KnowledgeBase, which owns approved answer content; the ConversationSession, which owns call state and escalation; and the VoicePipeline, which owns the speech in and speech out loop. The agent's public method handle_message() remains the single decision entry point.

## 3.3 Component status

| Component | Week 2 status | Notes |
| --- | --- | --- |
| Typed input STT stand-in | Implemented and tested | Returns the supplied text after trimming; rejects non-text input |
| Streaming STT (Deepgram, Azure, Google, Whisper) | Not connected | No credential or account available |
| Windows SAPI text-to-speech | Implemented and verified | 2 voices detected; COM object created; speak path exercised with silent input |
| Console text-to-speech | Implemented and tested | Used when no voice is available and in --silent mode |
| Telephony TTS (ElevenLabs, Azure Neural, Cartesia) | Not connected | Needs telephony and TTS access |
| Knowledge base | Implemented and tested | Five approved sample entries, keyword scoring, validation |
| Conversation session | Implemented and tested | Fallback counter, escalation, ended state, turn history, summary |
| Telephony gateway and phone number | Not connected | Needs provider account, number and webhook |
| CRM or database integration | Not started | Planned for Week 3 |
| Admin dashboard | Not started | Planned for Week 3 |
| Call recording and transcription storage | Not started | Needs the live call path first |

## 3.4 Data held in memory during a call

| Field | Type | Meaning |
| --- | --- | --- |
| FaqEntry.id | str | Stable identifier such as returns |
| FaqEntry.question | str | Approved question text, used for display |
| FaqEntry.answer | str | Approved answer spoken to the customer |
| FaqEntry.keywords | tuple of str | Lower-case phrases used for scoring |
| Turn.customer_message | str | The customer text for that turn |
| Turn.response | AgentResponse | The reply, intent and escalation flag |
| ConversationSession.fallback_count | int | Consecutive misunderstood turns |
| ConversationSession.escalated | bool | Whether a human handoff has been triggered |
| ConversationSession.ended | bool | Whether the call has been closed with a goodbye |

Nothing is written to disk, no audio is stored and no personal data leaves the machine.

# 4. Conversation Engine and Escalation

## 4.1 Knowledge base behaviour

The knowledge base is built from the same approved sample FAQ content used in Week 1, now represented as immutable FaqEntry objects. Each entry needs an id, an answer and at least one keyword; missing fields, blank answers, duplicate ids and non-mapping input raise ValueError when the base is created. Lookup lower-cases nothing itself: it expects the agent's normalised text, then counts how many of an entry's keywords appear as substrings. The highest score wins, and ties keep the earlier entry, so the result is deterministic and every answer can be traced to one approved entry.

The lookup never composes a new policy. If no entry scores above zero, the knowledge base returns None and the agent follows its fallback path. This is the same guardrail as Week 1: the agent must not invent delivery times, refunds or prices.

## 4.2 Turn handling

Intent priority is unchanged from Week 1 and remains covered by the Week 1 tests: direct order reference, then requested human handoff, then order-related requests, business hours, FAQs, greeting, goodbye and fallback. Week 2 wraps each call to handle_message() with the session logic below.

## 4.3 Escalation rule

ConversationSession counts consecutive turns whose intent is fallback or empty. A turn that the agent understands resets the counter to zero. When the counter reaches three, and the call has not already been escalated, the session replaces the reply with the standard transfer message and sets the escalation flag.

| Miss number | Customer experience | Agent action |
| --- | --- | --- |
| 1 | The normal fallback apology, offering order status, hours, FAQs or a human | Counter becomes 1; no transfer |
| 2 | The same fallback apology | Counter becomes 2; no transfer |
| 3 | "I'm sorry, I'm still having trouble understanding you." followed by the transfer sentence | Counter stays at 3, escalate flag set, session marked escalated |
| Any later miss | The normal fallback apology | No second automatic transfer; the call is already escalated |

Two cases are handled explicitly. Silence and whitespace count as misunderstandings, because the agent did not understand the customer. A handoff the customer asked for is not replaced by a second automatic transfer, because the session records that escalation already happened.

## 4.4 Handoff summary

ConversationSession.summary() returns a short note for the human who receives the call. It contains the number of customer turns, the distinct topics in the order they appeared, and the outcome: transferred, closed by the customer, or still in progress. This directly supports the plan's warm-transfer requirement that the customer should not have to repeat themselves.

The summary is text only and lives in memory. It has not yet been sent to a human agent line, because no telephony transfer exists.

## 4.5 Example escalation

The fixed demo conversation includes three unknown requests in a row. The agent answers the first two with the normal fallback, then transfers on the third:

Customer: Can you cancel my subscription?
Agent [fallback]: Sorry, I didn't quite understand that. I can help with order
status, business hours, delivery and returns questions, or connect you to a
human representative. Could you rephrase your question?

Customer: What is the weather in Karachi?
Agent [fallback]: Sorry, I didn't quite understand that. I can help with order
status, business hours, delivery and returns questions, or connect you to a
human representative. Could you rephrase your question?

Customer: Do you also sell laptops?
Agent [handoff]: I'm sorry, I'm still having trouble understanding you. I'm
connecting you to a human representative now. Our team is available Monday to
Friday from 9 AM to 6 PM; Saturday from 10 AM to 2 PM; closed on Sunday
(Asia/Karachi). A colleague will be with you shortly.

[system] Escalation flag set: hand this call to a human representative.

# 5. Voice Pipeline

## 5.1 Interfaces

| Interface | Member | Purpose |
| --- | --- | --- |
| SpeechToText | transcribe(audio) | Turn one piece of customer audio into text |
| TextToSpeech | speak(text) | Deliver the reply; returns False when it could not be delivered |
| VoicePipeline | handle_audio(audio) | Run one full turn and speak the reply |
| VoicePipeline | last_transcript | The text the session actually processed |
| VoicePipeline | last_delivered | Whether the last reply reached the customer |
| VoicePipeline | simulated(...) | Build the offline demo pipeline with automatic fallback |

The protocols are structural: any object with a matching method can replace the typed stand-in or the Windows voice. This is the seam where streaming speech-to-text and a telephony voice will be connected in a later week.

## 5.2 Speech-to-text stand-in

TypedInputSTT accepts text and returns it trimmed. It does not open a microphone, does not call a speech service and does not convert audio. The demo script and the interactive prompt supply the customer lines directly. The class is deliberately named so that nobody can mistake it for a working recognition engine.

## 5.3 Spoken output on this machine

SapiTextToSpeech uses the Windows built-in speech synthesizer. It runs the bundled Windows PowerShell with -NoProfile -NonInteractive, passes the reply text through standard input, creates a SAPI.SpVoice COM object, sets the rate and calls Speak. Text is never interpolated into the command string, so customer or approved content cannot inject a shell command. If PowerShell is missing, the COM object cannot be created or the process fails, speak() returns False instead of raising.

Verification performed this week: the SAPI COM object was created and reported 2 installed voices; the exact PowerShell script path was exercised with a space as input, which completed with no audible output and returned success. Audio playback of a full sentence was not triggered automatically during development, so the laptop did not make unexpected noise; the demo can be run by the reader to hear it.

This is local speech synthesis, not a telephone voice. It is mono, laptop-speaker audio with no telephony codec, no call recording and no barge-in.

## 5.4 Printed fallback

ConsoleTextToSpeech prints the reply as a [voice] ... line and reports it as delivered. The pipeline selects it when --silent is used or when the Windows voice is not available. Every command in this document that captured output used this mode, so the transcripts are exact text records rather than descriptions of audio.

## 5.5 Demo modes

python -m src.voice.demo               # fixed conversation, spoken locally
python -m src.voice.demo --silent      # fixed conversation, printed only
python -m src.voice.demo --interactive # type customer lines yourself

The fixed conversation has seven turns: greeting, order status, FAQ, two normal fallbacks, an automatic handoff and a goodbye. At the end the demo prints the session summary.

# 6. Implementation

## 6.1 Week 2 project structure

src/
├── agent.py                # unchanged public behaviour; now uses KnowledgeBase
├── knowledge_base.py       # NEW: FaqEntry and KnowledgeBase
├── session.py              # NEW: ConversationSession and Turn
├── cli.py                  # Week 1 text demo, still working
├── sample_data.py          # fictional orders, hours and FAQ content
└── voice/                  # NEW package
    ├── pipeline.py         # speech interfaces and VoicePipeline
    ├── stt.py              # TypedInputSTT stand-in
    ├── tts.py              # Windows SAPI and console output
    └── demo.py             # simulated call entry point
tests/
├── test_agent.py           # 27 Week 1 tests, unchanged
├── test_knowledge_base.py  # 14 new tests
├── test_session.py         # 12 new tests
└── test_voice_pipeline.py  # 12 new tests
docs/
├── week2_test_results.txt
└── week2_demo_transcript.txt

## 6.2 New module responsibilities

| File | Responsibility | Key functions |
| --- | --- | --- |
| src/knowledge_base.py | Validated approved FAQ content and deterministic lookup | FaqEntry.from_mapping, KnowledgeBase.find, KnowledgeBase.ids |
| src/session.py | Per-call state, escalation and handoff summary | ConversationSession.handle, summary, turns |
| src/voice/pipeline.py | Speech-to-text to session to speech-to-text loop | VoicePipeline.handle_audio, simulated |
| src/voice/stt.py | Typed input as the recognition stand-in | TypedInputSTT.transcribe, is_empty |
| src/voice/tts.py | Windows SAPI and printed output | SapiTextToSpeech.speak, ConsoleTextToSpeech.speak |
| src/voice/demo.py | Simulated call script and interactive mode | run_script, run_interactive |

## 6.3 Changes to Week 1 modules

| File | Change | Compatibility |
| --- | --- | --- |
| src/agent.py | Imports KnowledgeBase; FAQ lookup now goes through it; handoff_reply() is public so the session reuses the same transfer sentence | Same intents, same replies, same handle_message() signature; all 27 Week 1 tests pass unchanged |
| src/agent.py | find_faq() kept as a small public helper that returns a plain dictionary | Existing callers keep working; the agent itself no longer uses it |
| src/__init__.py | Exports ConversationSession, Turn, FaqEntry and KnowledgeBase | Additive only |
| README.md | Week 2 status, structure, commands, limitations and GitHub commit instructions added | Week 1 sections kept |

No Week 1 file was deleted and the master plan was not modified.

## 6.4 Code quality practices

Standard library only for runtime code; no package installation is needed to run or test the agent.

Type hints on public functions and classes, with from __future__ import annotations.

Frozen dataclasses for responses, FAQ entries and turns, so a turn cannot be edited after it is recorded.

Validation at the knowledge base boundary, where content enters the system.

Explicit errors for bad input: non-string messages, non-text audio, invalid fallback limits and malformed FAQ entries.

No secrets, tokens or phone numbers in the repository; PowerShell receives text through standard input, not through the command line.

The demo banner and every document state that the call is simulated.

## 6.5 Known implementation limits

The session keeps call state in memory only; it is lost when the process ends. The knowledge base matches substrings, so a keyword that appears inside an unrelated word could score a false hit; normalisation and word-boundary rules in the agent reduce but do not eliminate this. The SAPI voice is Windows-specific; other systems fall back to printed replies. The typed input stand-in bypasses all audio concerns, so it cannot reveal microphone, echo or codec problems.

# 7. Testing and Results

## 7.1 Test strategy

The suite uses the standard library unittest runner and stays compatible with pytest. Week 2 tests are grouped by module: knowledge base validation and lookup, session state and escalation, and voice pipeline with fake speech components so no audio is played. The Week 1 tests were not edited; they still run against the refactored agent.

## 7.2 Coverage by module

| Test area | Tests | What is verified |
| --- | --- | --- |
| Week 1 agent (test_agent.py) | 27 | Intents, order validation, hours summary, FAQs, handoff, fallback, empty input, response contract |
| Knowledge base (test_knowledge_base.py) | 14 | Entry validation, keyword normalisation, scoring, empty and unknown input, custom entries, duplicate ids |
| Session (test_session.py) | 12 | Fresh state, three-miss escalation, counter reset, silence counting, custom limit, requested handoff, goodbye, summary |
| Voice pipeline (test_voice_pipeline.py) | 12 | Full turn, transcript and delivery reporting, escalation through the pipeline, typed STT validation, console output, missing PowerShell, invalid rate |
| Total | 65 | All passing |

## 7.3 Representative new test cases

| ID | Scenario | Expected result |
| --- | --- | --- |
| W2-KB-01 | Load the sample knowledge base | Five entries, including returns |
| W2-KB-02 | Ask "how long does delivery take" | Entry shipping_time is returned |
| W2-KB-03 | Ask "delivery charge or free shipping" | Entry delivery_charges wins on keyword score |
| W2-KB-04 | Load an entry with no answer | ValueError is raised at load time |
| W2-KB-05 | Load two entries with the same id | ValueError is raised |
| W2-SS-01 | New session | Counter 0, not escalated, not ended, empty summary |
| W2-SS-02 | Two unknown requests, then a greeting, then one unknown request | Counter resets to 0 after the greeting, then becomes 1 |
| W2-SS-03 | Three unknown requests in a row | Handoff intent, escalation flag set, session escalated |
| W2-SS-04 | Three empty messages | Handoff intent and escalation, because silence counts |
| W2-SS-05 | Ask for a human, then miss three times | No second automatic transfer |
| W2-SS-06 | Send a goodbye, then another message | Session is ended; the next turn raises RuntimeError |
| W2-SS-07 | Greeting, order lookup, human request | Summary lists three turns, both topics and the transfer outcome |
| W2-VP-01 | One spoken turn through fake STT and TTS | Reply returned, TTS received exactly that reply, turn recorded |
| W2-VP-02 | TTS reports not delivered | last_delivered is False |
| W2-VP-03 | Three misses through the pipeline | Escalation still happens |
| W2-VP-04 | Non-text audio | TypeError is raised |
| W2-VP-05 | Missing PowerShell path | available and speak() return False without crashing |
| W2-VP-06 | Console back end | Reply is printed and reported as delivered |

## 7.4 Actual test results

Command run from the project root on 31 October 2026:

python -m unittest discover -s tests -t . -v

Actual output:

Ran 65 tests in 0.012s

OK

The same suite under pytest:

65 passed, 21 subtests passed in 0.17s

The full verbose output is saved in docs/week2_test_results.txt. The Week 1 evidence remains in docs/test_results.txt.

## 7.5 Demo verification

The fixed demo was run in silent mode and captured to docs/week2_demo_transcript.txt. It completed seven turns and finished with:

[system] Call summary: 7 customer turn(s); topics: greeting, order status, faq,
fallback, handoff, goodbye; outcome: transferred to a human representative.

The interactive mode was also exercised with piped input (Where is my order ORD-1003?, then exit). It returned the order status for ORD-1003 and ended the call cleanly.

## 7.6 Speech output verification

The Windows PowerShell path was confirmed: C:\Windows\System32\WindowsPowerShell\v1.0\powershell.exe.

The SAPI COM object was created and returned 2 installed voices.

The exact script used by SapiTextToSpeech was run with a space as input. It completed successfully with no audible output, proving the stdin, COM and Speak path without making noise.

Full-sentence audio playback was not triggered automatically. To hear it, run python -m src.voice.demo.

## 7.7 Defects found and fixed

| Defect | Cause | Fix | Verification |
| --- | --- | --- | --- |
| Pipeline non-text test failed with AttributeError | The fake STT called .strip() before the typed stand-in could validate the input | The test now uses TypedInputSTT, which raises the intended TypeError | Full suite green |
| Demo printed [voice] before the customer line and duplicated the input prompt | The reply was spoken before the transcript line, and interactive mode echoed the message twice | Customer line prints first; interactive mode reuses the terminal prompt instead of echoing | Both demo modes re-run |
| SAPI reported available for a custom path that does not exist | Availability checked only that a string was set | Availability now also requires the file to exist | test_missing_powershell_is_reported_not_crashed passes |

## 7.8 Remaining test gaps

No test plays real audio; the SAPI path was checked by construction and a silent input, not by listening.

No network call is tested, because no provider is connected.

No load or concurrency test; the session is single-call and in memory.

No Urdu or mixed-language test; the knowledge base and intents are English-first.

No latency test; the 1.5-second target is unmeasured.

No end-to-end telephony test; this remains the largest gap in the project.

# 8. Blockers and Access Checklist

## 8.1 Telephony and speech services

The environment still has no approved calling platform account, no phone number, no verified test destination, no public webhook and no speech-recognition credential. Environment variables for these services are empty. Nothing in the repository claims a live call or live recognition.

## 8.2 Access needed before the first real call

| Access or decision | Purpose | Status |
| --- | --- | --- |
| Telephony account (Twilio, Telnyx, Plivo or local SIP) | Place and receive calls, stream audio | Not available |
| Account credentials stored as environment variables | Authenticate API requests | Not available |
| One voice-capable phone number | Caller ID and inbound calls | Not available |
| One verified test destination number | Test calls on trial accounts | Not available |
| Public HTTPS webhook (for example ngrok) | Receive call and media events | Not available |
| Streaming STT key (Deepgram, Azure, Google or Whisper) | Recognise customer speech | Not available |
| Telephony TTS key (ElevenLabs, Azure Neural or Cartesia) | Natural voice on the phone line | Not available |
| LLM key (if free-form understanding is added) | Classify unusual phrasing | Not available |
| Client-approved recording notice, calling hours and Do-Not-Call policy | Compliance before any live call | Pending client and legal confirmation |
| Human agent number for warm transfer | Deliver the escalated call | Pending client |

## 8.3 Safe next integration steps

1.  Confirm the client-approved script, recording notice and calling window in writing.

2.  Obtain the telephony account, one number and one verified test destination.

3.  Replace TypedInputSTT with a streaming STT adapter and SapiTextToSpeech with the telephony TTS adapter; the session and dialogue code should not change.

4.  Place a single inbound test call to the project number, then a single outbound test call to the verified destination.

5.  Record the real latency, transcript and audio quality before widening the pilot.

6.  Connect the CRM or database only after the call path is stable.

# 9. Week 2 Progress Plan

| Day | Planned task | Actual output | Status |
| --- | --- | --- | --- |
| Day 6 | Move FAQ content into a validated knowledge base | FaqEntry, KnowledgeBase and 14 tests | Complete |
| Day 7 | Add call state, escalation and handoff summary | ConversationSession, Turn and 12 tests | Complete |
| Day 8 | Build the voice loop and local speech output | VoicePipeline, TypedInputSTT, SAPI and console TTS, demo | Complete |
| Day 9 | Integrate, run the suite and capture evidence | 65 tests passing, demo transcripts and test output saved | Complete |
| Day 10 | Document, update README and prepare the GitHub change list | Week 2 document, README section, commit instructions | Complete |
| Day 9 to 10 | Live speech recognition and a telephone test call | Not possible without provider access | Blocked |

# 10. Risks and Mitigations

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Telephony or STT access is delayed again | High | High | Keep every provider-dependent part behind an interface; the dialogue and session work is already proven |
| STT accuracy is poor for local accents and mixed Urdu and English | Medium | High | Test with real call recordings before the pilot; choose a provider using sample audio; keep the human handoff ready |
| Response latency exceeds the 1.5-second target | Medium | High | Measure each stage once real services are connected; stream STT and TTS rather than waiting for full sentences |
| Windows voice is mistaken for the production voice | Low | Medium | README, demo banner and this document all state that it is local laptop speech |
| Over-escalation annoys customers | Low | Medium | Three misses are required; a successful turn resets the counter; a requested handoff is not repeated |
| Keyword matching gives a wrong FAQ answer | Medium | Medium | Answers remain approved text only; add more keywords and review misses from pilot transcripts |
| Scope grows beyond one month | Medium | High | Week 3 and Week 4 items stay in the plan; new requests go through a change discussion |

# 11. Deliverables and Acceptance Checklist

| Deliverable | Status | Evidence |
| --- | --- | --- |
| Knowledge base module | Complete | src/knowledge_base.py |
| Call session with escalation | Complete | src/session.py |
| Voice loop and local speech output | Complete | src/voice package |
| Simulated call demo | Complete | python -m src.voice.demo |
| Automated tests | Complete | 65 tests, 0 failures |
| Captured test output | Complete | docs/week2_test_results.txt |
| Captured demo transcript | Complete | docs/week2_demo_transcript.txt |
| README updated for Week 2 | Complete | README.md, Week 2 status section |
| Week 2 Word document | Complete | This document |
| Live call and streaming STT | Blocked | Section 8 access checklist |
| Supervisor review and sign-off | Pending | Requires the reader's review |

# 12. Limitations and Deferred Work

| Limitation | Impact | Planned resolution |
| --- | --- | --- |
| Customer input is typed, not spoken | No microphone, accent or noise behaviour is exercised | Connect streaming STT when credentials arrive |
| Spoken output is local Windows SAPI | Voice quality and codec differ from a telephone line | Connect a telephony TTS provider |
| No barge-in | A customer cannot interrupt the agent mid-sentence | Implement with the real audio stream and echo handling |
| No latency measurement | The 1.5-second target is unproven | Instrument each pipeline stage during the first provider test |
| Session state is in memory | A restart loses the call and summary | Persist calls in the Week 3 database work |
| English-first content | Urdu and mixed-language customers may fall back | Add approved bilingual content and an STT model that covers both |
| No recording, transcript storage or dashboard | Supervisors cannot review calls yet | Week 3 logging and dashboard work |
| No CRM or calendar actions | Agent can only read sample data and FAQ content | Week 3 integration work |
| Handoff summary is not delivered to a human line | The transfer is simulated only | Connect the transfer leg with the telephony provider |

# 13. Conclusion

Week 2 turns the Week 1 decision layer into a call-level engine. The knowledge base now owns approved answers and rejects malformed content before a call begins. The session object remembers the call, counts repeated misunderstandings, escalates after three of them and prepares a summary for a human. The voice pipeline runs a complete turn and speaks the reply through the laptop's Windows voice, with a printed fallback and a clearly labelled typed-input stand-in.

All 65 automated tests pass, the simulated call completes seven turns including an automatic escalation, and the captured output is stored in the repository. The two plan items that are still open are the ones that need external access: streaming speech recognition and a real telephone call. They are documented as blocked, not claimed as done.

# Appendix A - Setup and Commands

# From the project root
# Week 1 text prototype
python -m src.cli
python -m src.cli --demo

# Week 2 simulated call
python -m src.voice.demo
python -m src.voice.demo --silent
python -m src.voice.demo --interactive

# Tests (standard library runner)
python -m unittest discover -s tests -t . -v

# Tests (optional pytest runner)
python -m pytest -q

# Rebuild this Word document from its Markdown source
python scripts/build_week2_document.py

# Appendix B - Week 2 Simulated Call Transcript

Captured from python -m src.voice.demo --silent on 31 October 2026. Replies are the exact approved text that the Windows voice would speak.

AI Customer Calling Agent - Week 2 simulated call
SIMULATED CALL: typed input, local speech output.
No phone line, no microphone and no recording are used.

Customer: Hello
[voice] Hello, and thank you for calling Sample Store Support. I'm an AI
assistant, and this call may be recorded. I can help with order status, business
hours and common questions. How can I help you today?
[intent] greeting

Customer: Where is my order ORD-1002?
[voice] Order ORD-1002 is marked as Processing. Payment is confirmed and the
order is being packed. Expected delivery: 2 November 2026. Is there anything
else I can help you with?
[intent] order_status

Customer: How long does delivery take?
[voice] Standard delivery takes 3 to 5 working days after dispatch. Orders
placed before 2 PM are usually dispatched the same working day. Is there
anything else I can help you with?
[intent] faq

Customer: Can you cancel my subscription?
[voice] Sorry, I didn't quite understand that. I can help with order status,
business hours, delivery and returns questions, or connect you to a human
representative. Could you rephrase your question?
[intent] fallback

Customer: What is the weather in Karachi?
[voice] Sorry, I didn't quite understand that. I can help with order status,
business hours, delivery and returns questions, or connect you to a human
representative. Could you rephrase your question?
[intent] fallback

Customer: Do you also sell laptops?
[voice] I'm sorry, I'm still having trouble understanding you. I'm connecting
you to a human representative now. Our team is available Monday to Friday from
9 AM to 6 PM; Saturday from 10 AM to 2 PM; closed on Sunday (Asia/Karachi).
A colleague will be with you shortly.
[intent] handoff
[system] Escalation flag set: hand this call to a human representative.

Customer: Okay, that's all. Thank you
[voice] You're welcome. Thank you for calling Sample Store Support. Goodbye!
[intent] goodbye

[system] Call summary: 7 customer turn(s); topics: greeting, order status, faq,
fallback, handoff, goodbye; outcome: transferred to a human representative.

# Appendix C - Week 2 Test Results

Ran 65 tests in 0.012s

OK

Module breakdown: Week 1 agent 27, knowledge base 14, session 12, voice pipeline 12. Under pytest the same suite reports 65 passed and 21 subtests passed. The full verbose listing is in docs/week2_test_results.txt.

# Appendix D - GitHub Change List

Week 2 additions for the repository:

src/knowledge_base.py
src/session.py
src/voice/__init__.py
src/voice/pipeline.py
src/voice/stt.py
src/voice/tts.py
src/voice/demo.py
tests/test_knowledge_base.py
tests/test_session.py
tests/test_voice_pipeline.py
docs/WEEK2_DEVELOPMENT_DOCUMENT.md
docs/week2_test_results.txt
docs/week2_demo_transcript.txt
scripts/build_week2_document.py
WEEK2_DEVELOPMENT_DOCUMENT.docx

Updated files:

src/agent.py
src/__init__.py
README.md
scripts/build_week1_document.py

Suggested commit message:

Week 2: call session, knowledge base and local voice loop

The files can be added to the existing repository without a zip archive. No secrets, tokens or phone numbers are included.